BEGINNER ROADMAP

Garage Project Skill Journeys

Pet Bot  •  Desk Buddy  •  More Tea / Navigational Robot

Purpose Give complete beginners a clear starting point, weekly build targets, and evidence they can show before joining project integration.

# How the programme works

- Weeks 1–2: everyone completes a small shared foundation in tools, wiring, coding, testing, and documentation.

- Then: each member chooses one primary track and one lighter secondary track connected to their project.

- Every stage ends with a working artefact—not only a watched video or completed reading.

- A mentor checks evidence every one or two weeks and redirects learners who are stuck.

Suggested workload About 3–5 hours each week: 1 hour learning, 2–3 hours building/debugging, and 30 minutes documenting.

Learn just enough → build → test → explain → integrate

# 1. What should a beginner do first?

Recommendation for member Start with ESP32 and PlatformIO immediately. Learn the small amount of C/C++ needed for each practical task instead of completing a long generic C++ course first.

## Hardware and software are connected

| Area | What it includes | Beginner evidence |
| --- | --- | --- |
| Hardware | ESP32 board, breadboard, wiring, sensors, motor driver, power, connectors, multimeter checks and safe grounding. | A labelled wiring diagram, voltage checks and a circuit that works reliably. |
| Firmware / software | PlatformIO project, C/C++ logic, pin configuration, functions, timing, serial messages, sensor filtering and state control. | Code that compiles, behaves correctly and can be explained line by line at a high level. |

## The C/C++ subset needed at the start

- Variables and types: int, float, bool and readable names.

- Conditions and loops: if/else, for and while—already similar to Python/C fundamentals.

- Functions: split sensing, decisions and actuation into small pieces.

- Timing: use millis() for millisecond scheduling and micros() for short intervals or pulse measurements; compare unsigned elapsed time (now - previous) so rollover is safe; avoid long delay() calls.

- Libraries and objects: begin by using them; learn deeper OOP only when the project requires it.

## Using AI without losing the learning

- Ask for an explanation and pseudocode before requesting code.

- Build and test one function at a time; do not paste an entire untested project.

- Change one pin, threshold or behaviour yourself and predict the outcome before uploading.

- Keep a short debug log: problem, test, result and next change.

- You are ready to move on only when you can explain the inputs, outputs, timing and safety assumptions.

# 2. Shared foundation — everyone

Outcome after two weeks The learner can open a project, read a simple wiring diagram, run a small program, use a terminal, record evidence and ask a useful debugging question.

## WEEK 1  Tools and basic coding   2–4 hours

Learn: VS Code; folders and file paths; terminal commands; variables, conditions, loops and functions; reading compiler errors.

Build: Create a small program that accepts a value, makes a decision and prints a clear result. ESP32 learners also create a PlatformIO project and upload Blink.

Evidence: Screenshot of the running program, source files and a five-sentence explanation.

## WEEK 2  Build, measure and document   3–5 hours

Learn: Voltage versus current; 3.3 V logic; common ground; input/output; breadboard rails; continuity and voltage measurement; safe power-off changes.

Build: Wire one input and one output. Example: button → LED or distance threshold → buzzer. Draw the wiring and record one fault you diagnosed.

Evidence: Short video, labelled diagram, code link and debug log.

## Choose a primary and secondary track

| Project | Recommended primary tracks | Useful secondary tracks | First integration target |
| --- | --- | --- | --- |
| Pet Bot | ESP32; PCB/electronics; LLM | 3D modelling; motor/sensor firmware | Detect an obstacle/table edge and issue a safe movement response. |
| Desk Buddy | LLM; ESP32; STS3215 | PCB/electronics; 3D modelling | User input produces an expression, response or servo motion. |
| More Tea | ROS 2 navigation; ROS 2 manipulation | ESP32; PCB; 3D; STS3215 | Teleoperate in simulation, then add mapping/navigation or arm motion. |

Allocation rule Use roughly 70% of learning time on the primary track and 30% on the secondary track. Do not assign a beginner to every skill at once.

## Learning from official documentation and open-source projects

Required method For every skill track: read the official documentation or maintained repository, run its smallest example, predict and make one change, verify the result with a measurement or log, then record the source URL and version or commit. Inspect the licence before copying or redistributing open-source code or designs.

Reusable LLM prompt: I am learning [topic] for [project]. Use [official documentation or repository URL] as the primary source and cite the relevant page, section or file. Explain the concept in beginner language, show the data or control flow, ask me to predict the result, and give one minimal exercise. Do not produce the complete project until I submit pseudocode. State version, hardware and licence assumptions, and say when the source does not support a claim.

| Skill track | Required official/open-source reading | Practical proof |
| --- | --- | --- |
| ESP32 | Arduino/ESP32 reference: millis(), micros(), rollover-safe elapsed-time checks, GPIO, PWM, UART and I2C. | Run a minimal timing test, change an interval, predict the result, then submit serial logs and the source links used. |
| PCB design | KiCad documentation plus component datasheets: schematics, symbols, footprints, ERC/DRC, track width and Gerber output. | Explain one datasheet decision, clear ERC/DRC or justify exceptions, and attach the manufacturing outputs. |
| 3D CAD / Fusion | Official Autodesk Fusion help for constrained sketches, parameters, joints, interference, tolerances and STEP/STL; study open-source CAD projects for design examples. | Modify one parameter, show the measured effect and interference check, and cite the help page or repository. Fusion itself is proprietary software. |
| LLM + voice | Project READMEs, model cards and licences for the local model, API, RAG, Vosk STT and Piper TTS; include version, context and hardware limits. | Reproduce a documented example, alter one setting, record RAM/latency and explain the microphone-to-speaker data flow. |
| ROS 2 navigation | ROS 2 and Nav2 docs: nodes, topics, services, actions, parameters, QoS, TF, URDF, cmd_vel, odom, LaserScan, SLAM and Nav2 configuration. | Inspect live topics/frames, change one documented parameter, predict the effect and provide a rosbag, log or screenshot. |
| ROS 2 manipulation | MoveIt and ros2_control docs: URDF, joints, controllers, planning groups, IK, collision checking and the simulator bridge. | Plan and execute a simulated motion, change one limit or target, and explain which configuration files control the result. |
| STS3215 servos | Manufacturer manual/register map plus a maintained open-source driver: bus voltage, IDs, baud rate, position units, limits, readback and error handling. | Discover one servo, command a safe limited move, read back its state and cite the register or driver code used. |

Microcontroller and PCB sources: Arduino millis()  |  Arduino micros()  |  Arduino reference  |  KiCad docs

CAD, LLM and voice sources: Autodesk Fusion help  |  FreeCAD repository  |  llama.cpp  |  Vosk  |  Piper

ROS 2 and robotics sources: ROS 2 Jazzy concepts  |  Nav2  |  MoveIt  |  ros2_control  |  STS3215 driver example

# 3. ESP32 microcontroller journey

Best fit Beginners who want hands-on electronics and coding. No prior C++ or OOP is required; Python/C fundamentals are enough to begin.

## 1  PlatformIO and first upload   Week 1

Learn: Project structure, board selection, setup(), loop(), serial monitor and pin definitions.

Build: Blink an LED and print a timed status message.

Evidence: Successful upload, serial screenshot and explanation of setup versus loop.

## 2  Inputs, outputs and safe wiring   Week 2

Learn: Pull-up/pull-down logic, buttons, LEDs, 3.3 V limits, common ground and multimeter checks.

Build: Button-controlled LED with debouncing or a sensor-controlled buzzer.

Evidence: Wiring diagram, measured voltage and a short demo.

## 3  Non-blocking robot behaviour   Week 3

Learn: millis() for millisecond scheduling, micros() for short intervals and pulse measurements, unsigned rollover-safe elapsed-time checks, state machines, thresholds and separate read/decide/act functions.

Build: Run two behaviours without blocking: schedule an LED or sensor with millis(), then use micros() to measure loop or pulse timing and print the results to Serial.

Evidence: Code using now - previous instead of long delay(), a timing log, one predicted interval change and links to the official millis()/micros() references.

## 4  Actuators and communication   Week 4

Learn: PWM, motor-driver direction pins, external motor power, UART/I²C basics and structured serial commands.

Build: Control one motor or servo safely and report a sensor value over serial.

Evidence: Power diagram, command list, current/temperature observation and stop behaviour.

## 5  Project mini-capstone   Weeks 5–6

Learn: Modular files, configuration constants, fault handling and integration testing.

Build: Pet Bot: edge/obstacle response. Desk Buddy: expression or servo controller. More Tea: wheel/encoder or actuator test interface.

Evidence: Repository/folder, readme, wiring, test video and known limitations.

Start here: PlatformIO ESP32 beginner tutorial  •  Getting Started with PlatformIO video

# 4. PCB and electronics journey

Scope This is broader than drawing a PCB. Learners must understand the circuit, power path, connectors, footprints, assembly and bring-up testing.

## 1  Read and recreate a circuit   Week 1

Learn: Symbols, nets, power rails, decoupling, connectors, polarity and datasheets.

Build: Recreate a simple LED/sensor interface schematic in KiCad.

Evidence: Annotated schematic and explanation of every component.

## 2  Footprints and design rules   Week 2

Learn: Symbol-to-footprint mapping, connector pin numbering, track width, clearance and board outline.

Build: Assign verified footprints and pass ERC before layout.

Evidence: ERC report plus footprint checks against datasheets.

## 3  PCB layout   Week 3

Learn: Placement, return paths, decoupling proximity, power routing, ground pours, mounting holes and silkscreen labels.

Build: Route a two-layer beginner board and pass DRC.

Evidence: DRC report and screenshots of both copper layers.

## 4  Manufacturing review   Week 4

Learn: Gerbers, drill files, BOM, polarity marks, assembly access and design-for-debug test points.

Build: Generate fabrication outputs and conduct a peer checklist review.

Evidence: Gerber viewer screenshot, BOM and resolved review comments.

## 5  Assembly and bring-up   When hardware arrives

Learn: Inspection before power, continuity, current-limited supply, rail-by-rail testing and fault isolation.

Build: Bring up the board without connecting expensive loads first.

Evidence: Bring-up log with expected/actual voltages and any rework.

Resources: KiCad layout in five steps  •  KiCad 8 beginner walkthrough

Safety gate A mentor must approve power architecture, connector pinout and motor/battery interfaces before the learner orders or powers a board.

# 5. 3D modelling journey

Goal Create parts that fit real components, can be assembled and can be revised when measurements change—not only attractive renders.

## 1  Sketches and constraints   Week 1

Learn: Units, origin, fully constrained sketches, dimensions, extrude, cut and fillet.

Build: Model a simple sensor or ESP32 mounting plate.

Evidence: Fusion file with named sketches and correct key dimensions.

## 2  Component-driven design   Week 2

Learn: Caliper measurement, clearances, hole sizes, fasteners, connectors and cable access.

Build: Create a holder around a real component and include assembly clearance.

Evidence: Photo of component, measurement sheet and fit-test result.

## 3  Assemblies and iteration   Week 3

Learn: Components, joints, interference checks, parameters and versioned changes.

Build: Assemble two or more parts digitally and correct one detected clash.

Evidence: Before/after screenshots and brief design rationale.

## 4  Fabrication-ready part   Week 4

Learn: Print orientation, wall thickness, tolerances, inserts, support reduction and export formats.

Build: Print or fabricate one project part, test it and revise once.

Evidence: STEP/STL, drawing or key dimensions, fit-test video and revision note.

Resources: Fusion 360 beginner guide  •  Useful Fusion shortcuts

# 6. LLM and interaction journey

Required environment Use Debian in WSL 2 and cap the WSL 2 virtual machine at 8 GB RAM. This reproduces a constrained development environment, but it does not reproduce Raspberry Pi ARM performance exactly.

Required final interaction A user speaks through the computer microphone; speech-to-text produces the query; approved Garage@EEE information is retrieved; the lightweight LLM creates a grounded answer; text-to-speech plays it through the computer speaker.

## One-time Windows and audio setup

- In an Administrator PowerShell window, install Debian with: wsl --install -d Debian

- Create %UserProfile%\.wslconfig in Windows and add [wsl2] on one line and memory=8GB on the next. Optional: processors=4 and swap=2GB.

- Apply the cap with wsl --shutdown, reopen Debian, then verify inside Linux with free -h.

- Remember that .wslconfig applies to the WSL 2 virtual machine globally, so other running WSL 2 distributions share this limit.

- Test the computer microphone and speaker by recording and replaying a short clip. For the most reliable beginner setup, the Windows audio client may call the LLM/RAG service in WSL through localhost; use WSLg audio only when both devices are detected reliably.

## 1  Linux and Python workflow   Week 1

Learn: Debian shell, apt, files, permissions, Git, Python virtual environments and dependency files.

Build: Clone a small repository, create a virtual environment and run a Python script from the terminal.

Evidence: Command log and requirements file.

## 2  Run a small local model   Week 2

Learn: Ollama installation, model size, context length, memory use, prompts and response latency.

Build: Run a small quantized 0.5B-1.5B model that stays within the 8 GB cap; record RAM and response time.

Evidence: Model name, test prompts, free -h output and observations.

## 3  Programmatic interaction   Week 3

Learn: Local API requests, JSON, system prompts, timeouts and parsing model output.

Build: Write a Python client that sends a prompt and returns a structured response.

Evidence: Working script and three repeatable tests.

## 4  Garage website content pipeline   Week 4

Learn: Static versus JavaScript-rendered pages, public web content, HTML/JSON cleaning, source metadata, approval and versioning. Retrieval-augmented generation (RAG) uses selected information; it does not retrain the model.

Build: Extract approved public information from the Garage@EEE website and official NTU Garage page into Markdown or JSON. Save the source URL and last-updated or retrieval date with every entry.

Evidence: Extraction script, cleaned knowledge files and a content-review checklist.

## 5  Retrieval and grounded answers   Week 5

Learn: Chunking, keyword/SQLite FTS or BM25 retrieval, optional embeddings, source display, hallucination control and fallback answers.

Build: Retrieve the most relevant approved passages before every answer. Display the source and refuse questions not supported by the knowledge base.

Evidence: Retrieved passages, source links and tests for supported and unsupported questions.

## 6  Computer microphone and speaker loop   Week 6

Learn: Audio-device selection, sample rate, push-to-talk or voice-activity detection, speech-to-text (STT), text-to-speech (TTS), playback, feedback prevention and timeouts.

Build: Create the complete loop: computer microphone -> STT -> retrieval -> LLM -> TTS -> computer speaker. Show the transcript and retrieved source on screen. Use push-to-talk first so the microphone does not re-record the speaker.

Evidence: Live voice demo, audio-device configuration and an end-to-end latency table.

## 7  Robot-safe response layer   Week 7

Learn: Allowed intents, schema validation, deterministic commands, fallback responses and separation between conversation and motor control.

Build: Map supported answers to approved screen expressions, sounds or limited actions. Reject unsupported actions; never place the LLM inside the motor-stop or emergency-stop loop.

Evidence: Test table showing valid, ambiguous and rejected inputs.

## 8  Project integration and evaluation   Week 8

Learn: Lightweight architecture, logging, offline behaviour, latency budgeting and repeatable evaluation.

Build: Integrate the voice assistant with the Desk Buddy or Pet Bot response/display layer and complete the 10-question spoken evaluation sheet below.

Evidence: 10-question results, 30-90 second demo, memory/latency table, architecture sketch and known limitations.

## Grounding and answer policy

- Answer briefly using only retrieved, approved Garage@EEE information and show the source used.

- When evidence is missing, say: I could not find this information in the Garage@EEE knowledge base.

- Do not invent event dates, contacts, application procedures, equipment availability or portfolio responsibilities.

- Keep a last-updated or retrieval date for every website entry and flag content that needs review.

- Use public information only; do not collect unnecessary personal information.

## 10-question spoken evaluation sheet

Method: Speak each question through the computer microphone. Mark a question as passed only when the speech is transcribed correctly, a relevant approved source is retrieved, the answer contains no unsupported claim and the response is played clearly through the computer speaker.

| # | Spoken test question | Expected retrieval or behaviour | Pass checks |
| --- | --- | --- | --- |
| 1 | What is Garage@EEE? | Retrieve the official introduction and give a short sourced description. | STT [ ] Source [ ] Grounded [ ] Voice [ ] |
| 2 | Who does Garage@EEE support? | Use the approved Garage/NTU source and avoid adding eligibility rules that are not stated. | STT [ ] Source [ ] Grounded [ ] Voice [ ] |
| 3 | What is Garage@EEE's mission and vision? | Retrieve the official mission/vision content and summarise it accurately. | STT [ ] Source [ ] Grounded [ ] Voice [ ] |
| 4 | What facilities or support does Garage provide? | Use the current approved facilities/support page; do not invent equipment availability. | STT [ ] Source [ ] Grounded [ ] Voice [ ] |
| 5 | What is Enitio? | Retrieve the official event description and answer briefly. | STT [ ] Source [ ] Grounded [ ] Voice [ ] |
| 6 | What is Escendo? | Retrieve the official event description and answer briefly. | STT [ ] Source [ ] Grounded [ ] Voice [ ] |
| 7 | What is IdeasJam? | Retrieve the official event description and answer briefly. | STT [ ] Source [ ] Grounded [ ] Voice [ ] |
| 8 | What is STARTathon? | Retrieve the official event description and answer briefly. | STT [ ] Source [ ] Grounded [ ] Voice [ ] |
| 9 | What is the Innovation Festival? | Retrieve the official event description and answer briefly. | STT [ ] Source [ ] Grounded [ ] Voice [ ] |
| 10 | What time is the next Garage committee meeting? | If this is absent from the approved corpus, use the required 'could not find' fallback. | STT [ ] Source [ ] Grounded [ ] Voice [ ] |

Suggested pass condition: At least 8 of 10 questions pass all four checks, and Question 10 must use the fallback when the requested information is absent.

Official setup: WSL overview  |  WSL memory configuration  |  Ollama for Linux

Approved Garage sources: Garage@EEE website  |  NTU Garage@EEE page

# 7. ROS 2 navigation journey — More Tea

End goal Teleoperate a simulated mobile robot, visualise its sensors and transforms, build a map, and send a navigation goal before integrating real More Tea hardware.

## 1  ROS 2 foundations   Weeks 1–2

Learn: Workspace, packages, nodes, topics, messages, services, actions, launch files and parameters.

Build: Run talker/listener examples, inspect topics and create one small publisher/subscriber.

Evidence: Commands, package and explanation of data flow.

## 2  Robot model and frames   Week 3

Learn: URDF/Xacro, links, joints, robot_state_publisher, TF tree and RViz displays.

Build: Load a simple mobile robot and correctly display base, wheels and sensors.

Evidence: RViz screenshot and TF tree with no unexplained frame errors.

## 3  Simulation and teleoperation   Week 4

Learn: Gazebo world, plugins/controllers, cmd_vel, odometry and LaserScan.

Build: Drive the robot with keyboard or Bluetooth controller and verify odometry/scan topics.

Evidence: Video, topic list and plotted/observed odometry.

## 4  SLAM and Nav2   Weeks 5–6

Learn: Mapping, map saving, localisation, costmaps, planners, recovery behaviours and goals.

Build: Map a small world, restart with the saved map and navigate to three goals.

Evidence: Map files, screenshots and success/failure notes for three trials.

## 5  Linorobot2 / More Tea bridge   Weeks 7–8

Learn: Hardware interfaces, wheel geometry, encoder feedback, IMU/LiDAR data, controller tuning and simulation-to-real differences.

Build: Document the interface contract between the low-level controller and ROS 2; then validate one real sensor or drive subsystem safely.

Evidence: Interface table, launch/config files, test log and emergency-stop procedure.

Resources: ROS 2 Humble documentation  •  Linorobot2

# 8. ROS 2 manipulation journey — More Tea

End goal Plan and execute a collision-aware inverse-kinematics motion for a simulated SO-101 arm in Gazebo, or Isaac Sim when a suitable NVIDIA GPU is available.

## 1  ROS 2 and RViz essentials   Weeks 1–2

Learn: Nodes, topics, actions, launch files, parameters, TF and RViz.

Build: Inspect a running robot and explain how joint state data reaches RViz.

Evidence: Topic/frame screenshots and short data-flow explanation.

## 2  Robot description   Week 3

Learn: URDF/Xacro, joint types, limits, collision geometry and ros2_control concepts.

Build: Load the SO-101 description and inspect every joint and frame.

Evidence: Robot model, TF tree and joint-limit checklist.

## 3  MoveIt 2   Weeks 4–5

Learn: Planning groups, end effectors, planning scene, IK, collision checking and execution interfaces.

Build: Use the MoveIt Setup Assistant or understand the generated configuration; plan several poses in RViz.

Evidence: Configuration package and screenshots of valid and invalid plans.

## 4  Gazebo or Isaac Sim   Week 6

Learn: Controllers, joint-state feedback, spawn/launch flow and simulator bridge.

Build: Execute a planned arm trajectory in simulation and verify actual versus target joint motion.

Evidence: Launch files, video and joint-state evidence.

## 5  Final manipulation challenge   Weeks 7–8

Learn: Pose targets, collision objects, repeatable launch and failure recovery.

Build: Move the simulated end effector between two poses while avoiding one obstacle; reset and repeat successfully.

Evidence: One-command launch, source/config files, video, README and known limitations.

Resources: MoveIt 2 getting started  •  SO-101 MoveIt / Isaac Sim reference

# 9. STS3215 servo journey

Best fit Desk Buddy motion and later manipulation work. Begin on the bench with one unloaded servo before connecting a mechanism.

## 1  Power and bus setup   Week 1

Learn: Servo voltage/current, serial bus topology, controller interface, ID, baud rate and common ground.

Build: Identify and ping one servo using a current-limited supply.

Evidence: Power diagram, detected ID and measured idle behaviour.

## 2  Position and limits   Week 2

Learn: Position units, direction, speed/acceleration, limits, readback and safe neutral pose.

Build: Move between three conservative positions and read back position each time.

Evidence: Command table, video and limit justification.

## 3  Multiple servos   Week 3

Learn: Unique IDs, coordinated commands, cable strain relief, load and fault response.

Build: Control two servos in a repeatable sequence with a software stop.

Evidence: Wiring, code, temperature/current observations and stop test.

## 4  Project motion   Week 4

Learn: Motion state machine, calibration offsets, mechanical interference and startup/shutdown poses.

Build: Desk Buddy: expressive motion. More Tea arm: one low-risk joint test before full system integration.

Evidence: Calibration file, demo and collision/limit checklist.

Resource: STS3215 multi-part tutorial

Safety gate Never power servos through a computer USB port, never assume the default ID/baud rate, and keep hands clear when the mechanism is first enabled.

# 10. Project integration capstones

Integration rule A capstone should combine only two or three subsystems at first. Demonstrate a safe, repeatable behaviour before adding more features.

## Pet Bot — table-safe autonomous response

- Input: ultrasonic obstacle sensing plus table-edge sensing.

- Decision: non-blocking ESP32 state machine chooses forward, stop, reverse or turn.

- Output: DC motor driver commands with an always-available stop condition.

- Optional second layer: constrained LLM response or expression after the motion system is independently safe.

- Pass condition: 10 trials without falling, collision or uncontrolled restart; record failures honestly.

## Desk Buddy — interaction to expression

- Input: button, touch, typed prompt or approved voice/text intent.

- Decision: simple validated intent—not unrestricted model output controlling motors directly.

- Output: screen expression, sound or limited STS3215 motion.

- Pass condition: five supported interactions behave consistently; ambiguous input falls back safely.

## More Tea — navigate, then manipulate

- Navigation first: teleoperate, map, localise and reach a goal in simulation.

- Manipulation second: plan and execute an SO-101 end-effector motion around an obstacle.

- Integration later: define a clear hand-off—the base reaches a pose, stops and confirms stability before arm motion begins.

- Pass condition: repeat the complete simulated sequence three times from a clean launch.

What not to combine yet Do not begin with LLM + vision + navigation + manipulation + custom PCB simultaneously. Integrate one tested interface at a time.

# 11. Checkpoints, evidence and mentor reviews

## What every learner submits

- A short README: goal, setup, wiring/dependencies, how to run, expected result and known issues.

- Source files and configuration—not screenshots alone.

- A labelled wiring or architecture diagram appropriate to the role.

- A 30–90 second demonstration video or simulator recording.

- A debug log containing at least one failed attempt and how it was investigated.

- A two-minute explanation without reading AI-generated text word-for-word.

## Mentor rhythm

| Check-in | Learner shows | Mentor decides |
| --- | --- | --- |
| Start | Chosen primary/secondary tracks, available hardware and weekly availability. | Confirm a realistic first deliverable. |
| Every 1–2 weeks | Working artefact, evidence, blocker and next test. | Advance, simplify or pair the learner. |
| Before hardware power | Power diagram, pinout, expected voltages/current and stop procedure. | Approve or require corrections. |
| Capstone | Repeatable demo, source, README, test results and limitations. | Ready for project integration or another focused iteration. |

## Definition of ready

A learner is ready for team integration when they can reproduce the result from a clean start, explain the main data/power flow, identify safety limits, change one parameter independently, and describe what remains unreliable.

## Source resources from the original skills document

VS Code beginner tutorial

Autonomous OS reference

Pet Bot project reference

Garage database